## Sheet1
Timing
Days per Week | 5
Hours per Day | 7
Hours per Week | 35
Requested Hours for Whole Project | 595 | Estimated Hours Required | 1193.5
Staff
Name | Job Desc | Tasks | Pay (Hourly) | Hours | Days
Sarah O'Toole | Senior Software Engineer | Module 4 | 105 | 115 | 17
|  | Fixing Major Fault (x2) |  | 28 | 4
|  | Create Test Plan |  | 8 | 2
|  | Unit Testing |  | 21 | 3
|  | Integration Testing |  | 14 | 2
|  | Minor Fault (x6) |  | 42 | 6
|  | Deploy Module |  | 7 | 1
|  |  | TOTAL HOURS | 235
|  | TOTAL PAY | 24675
Ahad Shafiq | Junior Software Engineer | Module 3 | 25 | 126 | 18
|  | User/Acceptance Testing |  | 35 | 5
|  | Unit Testing (x1.5) |  | 31.5 | 5
|  | Integration Testing (x1.5) |  | 21 | 3
|  | Minor Fault (x3) |  | 21 | 3
|  | Deploy Module (x2) |  | 14 | 2
|  | Module 5 (1 quarter) |  | 28 | 4
|  | Create Test Plan |  | 2 | 1
|  |  | TOTAL HOURS | 278.5
|  | TOTAL PAY | 6962.5
Terry Duran | Junior Software Engineer | Module 5 (three quarters) | 45 | 84 | 12
|  | User Training |  | 21 | 3
|  | Module 2 |  | 70 | 10
|  | Unit Testing (x1.5) |  | 31.5 | 5
|  | Integration Testing (x1.5) |  | 21 | 3
|  | Minor Fault (x3) |  | 21 | 3
|  | Deploy Modules (x1.5) |  | 10.5 | 2
|  | Create Test Plan |  | 2 | 1
|  |  | TOTAL HOURS | 261
|  | TOTAL PAY | 11745
Gina Diaz | Database Engineer | Module 1 | 47.5 | 147 | 21
|  | Fixing Major Fault |  | 14 | 2
|  | Create Test Plan |  | 3 | 1
|  | Unit Testing |  | 21 | 3
|  | Integration Testing |  | 14 | 2
|  | Minor Fault (x3) |  | 21 | 3
|  | Deploy Modules |  | 7 | 1
|  |  | TOTAL HOURS | 227
|  | TOTAL PAY | 10782.5
Marius Bronski | Network Engineer | Module 6 | 73 | 105 | 15
|  | Upgrade Infrastructure |  | 21 | 3
|  | Create Test Plan |  | 3 | 1
|  | Unit Testing |  | 21 | 3
|  | Integration Testing |  | 14 | 2
|  | Minor Fault (x3) |  | 21 | 3
|  | Deploy Modules |  | 7 | 1
|  |  | TOTAL HOURS | 192
|  | TOTAL PAY | 14016
|  | TOTAL STAFF PAY | 68181
Financial Plan
Software Development Base Fee | 50000
Cost of training internal staff | 4000
Cost of equipment upgrades | 5000
Cost of new server (Option 1) | 230 | p/m
Cost of infrastructure Upgrades | 3200
Project Leaders Pay | 200 | p/d
Additional Network Technician | 22000
Maintenance Costs | 2250
TOTAL | 86880